Sensitive Species Extension Task Group Annual Report

Web Site:  Sensitive Species Extension - TDWG

| Convener(s): |  |
| --- | --- |
| Name | Email Address |
| Cameron Slatyer | cam.slatyer@csiro.au |

Submitted: 12 March 2026 (2025 Deadline missed)

Phase of work:

- Developing draft standard

Activities:

- The Task Group met five times (each 1 hour duration) between December 2024- November 2026 with a further two meetings (1 hour duration) held by subgroups focused on developing treatments for Darwin Core Native and the Darwin Core Data Package. Attendance and topics for each meeting are available from the Task Group GitHub repository (tdwg/sensitive-species-extension: A Task Group of the Darwin Core Maintenance Group).

- A draft set of Restricted Access Species Data sensitivity classes and treatments, together with examples and reasons, was developed over the first half of the year.

- In the second half of the year, the Task Group delegated two sub groups to try to use the sensitivity and treatment classes to develop technical solutions for Darwin Core Native and Darwin Core Data Packages

Accomplishments:

A draft set of Restricted Access Species Data sensitivity classes and treatments, together with examples and reasons

Draft technical implementations for both Darwin Core Native and Darwin Core Data Packages

Impediments to progress:

Nil

Changes in goals or scope

The Task group formally decided to change the descriptor from “Sensitive Species Data” to “Restricted Access Species Data” because there was a consensus view that this more clearly defined the intent of the Extension. This technically does not change either goals or scope but is included here for clarity.

Plans for next calendar year

Develop a working draft and documentation for consideration by the Executive Committee

Host a session at TDWG 2026 on implementation of RASD

Possibly hold a working session on the side of TDWG 2026